## BASE DATA (wajib update)
NO | KONTRAK | NOMOR DOKUMEN & NO. KONTRAK | JENIS PEKERJAAN | AREA PEKERJAAN | SUB AREA PEKERJAAN | CONCATE PEKERJAAN | PRIORITY | START | PLAN END | ACTUAL END | % COMPLETE | STATUS | Project Start | Days to Start | Complete | Incomplete | Slippage | Plan Days | SISA DURASI KONTRAK | BOBOT
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | PROJECT 1 A PEKERJAAN STRUKTURGENERAL | HIGH | 2024-07-05 | 2025-09-03 | 2025-06-15 | 72.24% | Dalam Proses | 2024-06-01 | 34 | 307.02 | 117.98 | -80 | 425 | 73 | 5
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEMBERSIHAN LAHAN | PEMBERSIHAN LAHAN | PROJECT 1 A PEKERJAAN STRUKTURPEMBERSIHAN LAHAN | LOW | 2024-07-05 | 2024-08-25 | 2025-06-15 |  | Selesai | 2024-06-01 | 34 | 0 | 51 | 294 | 51 | -302 | 0
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | LAND GRADING GALIAN & BUANGAN | LAND GRADING GALIAN & BUANGAN | PROJECT 1 A PEKERJAAN STRUKTURLAND GRADING GALIAN & BUANGAN | HIGH | 2024-08-11 | 2025-01-12 | 2025-06-15 | 78.77% | Dalam Proses | 2024-06-01 | 71 | 121.3058 | 32.6942 | 154 | 154 | -162 | 1.8587
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN MASUK | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN PEKERASAAN JALAN MASUK | LOW | 2024-09-30 | 2025-02-09 | 2025-06-15 | 0% | Tunda | 2024-06-01 | 121 | 0 | 132 | 126 | 132 | -134 | 0.79195
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN PEKERASAAN JALAN KAWASAN & AREA‐ | LOW | 2025-03-10 | 2025-04-08 | 2025-06-15 | 12.46% | Tunda | 2024-06-01 | 282 | 3.6134 | 25.3866 | 68 | 29 | -76 | 1.8582
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE JALAN MASUK & KAWASAN | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN DRAINASE JALAN MASUK & KAWASAN | MEDIUM | 2025-04-07 | 2025-05-04 | 2025-06-15 | 28.07% | Dalam Proses | 2024-06-01 | 310 | 7.5789 | 19.4211 | 42 | 27 | -50 | 0.4507
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PEKERJAAN & DRAINASE | PEKERJAAN DRAINASE IPAL & PANEN | PROJECT 1 A PEKERJAAN STRUKTURPEKERJAAN DRAINASE IPAL & PANEN | LOW | 2025-05-05 | 2025-06-01 | 2025-06-15 | 19.45% | Tunda | 2024-06-01 | 338 | 5.2515 | 21.7485 | 14 | 27 | -22 | 6.4714
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | PAGAR PANEL | PAGAR PANEL | PROJECT 1 A PEKERJAAN STRUKTURPAGAR PANEL | MEDIUM | 2024-08-26 | 2025-05-04 | 2025-06-15 | 33.06% | Tunda | 2024-06-01 | 86 | 82.9806 | 168.0194 | 42 | 251 | -50 | 2.1938
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | SEA WATER INTAKE | SEA WATER INTAKE | PROJECT 1 A PEKERJAAN STRUKTURSEA WATER INTAKE | MEDIUM | 2024-09-23 | 2024-12-22 | 2025-06-15 | 45.72% | Dalam Proses | 2024-06-01 | 114 | 41.148 | 48.852 | 175 | 90 | -183 | 1.4899
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | POND (12 unit) | PROJECT 1 A PEKERJAAN STRUKTURPOND (12 unit) | LOW | 2024-07-22 | 2025-06-22 | 2025-06-15 | 1.21% | Terlambat | 2024-06-01 | 51 | 4.0535 | 330.9465 | -7 | 335 | -1 | 33.0584
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | NURSERY POND (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURNURSERY POND (4 unit) | LOW | 2024-12-16 | 2025-06-22 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 198 | 0 | 188 | -7 | 188 | -1 | 1.8989
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | SKIMER POND (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURSKIMER POND (4 unit) | LOW | 2024-10-21 | 2025-02-16 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 142 | 0 | 118 | 119 | 118 | -127 | 0.61599
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | CONTROL ROOM & BLOWER (4 unit) | PROJECT 1 A PEKERJAAN STRUKTURCONTROL ROOM & BLOWER (4 unit) | LOW | 2025-02-10 | 2025-04-13 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 254 | 0 | 62 | 63 | 62 | -71 | 0.42275
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | OPERATOR HOUSE (2 unit) | PROJECT 1 A PEKERJAAN STRUKTUROPERATOR HOUSE (2 unit) | LOW | 2025-02-10 | 2025-04-20 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 254 | 0 | 69 | 56 | 69 | -64 | 0.054312
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | POND AREA | IPAL | PROJECT 1 A PEKERJAAN STRUKTURIPAL | MEDIUM | 2024-07-22 | 2025-05-11 | 2025-06-15 | 43.85% | Dalam Proses | 2024-06-01 | 51 | 128.4805 | 164.5195 | 35 | 293 | -43 | 0.74005
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN STRUKTURRESEARCH CENTER ROOM | LOW | 2025-04-28 | 2025-05-11 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 331 | 0 | 13 | 35 | 13 | -43 | 0.17748
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | DEEPWELL PUMP ROOM (DWP) | PROJECT 1 A PEKERJAAN STRUKTURDEEPWELL PUMP ROOM (DWP) | HIGH | 2024-11-11 | 2025-02-09 | 2025-06-15 | 99.97% | Tunda | 2024-06-01 | 163 | 89.973 | 0.027 | 126 | 90 | -134 | 0.03925
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUPMP ROOM SWI | PROJECT 1 A PEKERJAAN STRUKTURPUPMP ROOM SWI | LOW | 2025-01-13 | 2025-02-09 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 226 | 0 | 27 | 126 | 27 | -134 | 0.049777
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | FACILITY AREA | POWER HOUSE & WEEKLY TANK | PROJECT 1 A PEKERJAAN STRUKTURPOWER HOUSE & WEEKLY TANK | LOW | 2024-10-21 | 2025-05-04 | 2025-06-15 | 14.86% | Tunda | 2024-06-01 | 142 | 28.977 | 166.023 | 42 | 195 | -50 | 1.9867
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | PLATFORM RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN STRUKTURPLATFORM RESEARCH CENTER ROOM | LOW | 2024-12-16 | 2025-06-15 | 2025-06-15 | 9.69% | Belum Mulai | 2024-06-01 | 198 | 17.5389 | 163.4611 | 0 | 181 | -8 | 8.0827
1 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN STRUKTUR | OFFSHORE AREA | TANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | PROJECT 1 A PEKERJAAN STRUKTURTANGGA AKSES AREA RESEARCH CENTER ROOM (DERMA‐ | LOW | 2025-05-26 | 2025-06-15 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 359 | 0 | 20 | 0 | 20 | -8 | 0.048862
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | CONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | PROJECT 1 A PEKERJAAN ARSITEKTURCONTROL ROOM & BLOWER HOUSE (4 UNIT)‐ | LOW | 2025-02-24 | 2025-04-20 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 268 | 0 | 55 | 56 | 55 | -64 | 0.22891
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | POND AREA | OPERATOR HOUSE (2 UNIT)‐ | PROJECT 1 A PEKERJAAN ARSITEKTUROPERATOR HOUSE (2 UNIT)‐ | LOW | 2024-12-23 | 2025-04-13 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 205 | 0 | 111 | 63 | 111 | -71 | 0.074967
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | POWER HOUSE | PROJECT 1 A PEKERJAAN ARSITEKTURPOWER HOUSE | LOW | 2025-01-20 | 2025-06-15 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 233 | 0 | 146 | 0 | 146 | -8 | 0.41565
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | RESEARCH CENTER ROOM | PROJECT 1 A PEKERJAAN ARSITEKTURRESEARCH CENTER ROOM | LOW | 2025-05-12 | 2025-06-22 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 345 | 0 | 41 | -7 | 41 | -1 | 0.34221
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DEEPWELL PUMP ROOM | PROJECT 1 A PEKERJAAN ARSITEKTURDEEPWELL PUMP ROOM | LOW | 2024-08-26 | 2025-01-26 | 2025-06-15 | 20.93% | Tunda | 2024-06-01 | 86 | 32.0229 | 120.9771 | 140 | 153 | -148 | 0.020404
2 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE SWI | PROJECT 1 A PEKERJAAN ARSITEKTURPUMP HOUSE SWI | LOW | 2025-02-03 | 2025-03-09 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 247 | 0 | 34 | 98 | 34 | -106 | 0.023371
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | GENERAL | GENERAL | PROJECT 1 A PEKERJAAN ELEKTRIKALGENERAL | LOW | 2025-01-13 | 2025-06-29 | 2025-06-15 | 4.78% | Belum Mulai | 2024-06-01 | 226 | 7.9826 | 159.0174 | -14 | 167 | 7 | 2.9188
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | RESEARCH CENTER ROOM & SWI‐ | PROJECT 1 A PEKERJAAN ELEKTRIKALRESEARCH CENTER ROOM & SWI‐ | LOW | 2025-03-17 | 2025-08-03 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 289 | 0 | 139 | -49 | 139 | 42 | 0.11597
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | CONTROL ROOM & BLOWER HOUSE 1 s/d 4 | PROJECT 1 A PEKERJAAN ELEKTRIKALCONTROL ROOM & BLOWER HOUSE 1 s/d 4 | LOW | 2025-02-24 | 2025-04-27 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 268 | 0 | 62 | 49 | 62 | -57 | 0.081748
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OPERATOR HOUSE 1 s/d 2 | PROJECT 1 A PEKERJAAN ELEKTRIKALOPERATOR HOUSE 1 s/d 2 | LOW | 2025-02-17 | 2025-03-09 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 261 | 0 | 20 | 98 | 20 | -106 | 0.043968
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DEEP WELL PUMP ROOM | PROJECT 1 A PEKERJAAN ELEKTRIKALDEEP WELL PUMP ROOM | LOW | 2024-10-14 | 2025-03-09 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 135 | 0 | 146 | 98 | 146 | -106 | 0.012092
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | POWER HOUSE | PROJECT 1 A PEKERJAAN ELEKTRIKALPOWER HOUSE | LOW | 2024-12-23 | 2025-01-26 | 2025-06-15 | 10.56% | Belum Mulai | 2024-06-01 | 205 | 3.5904 | 30.4096 | 140 | 34 | -148 | 2.2129
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | GENERAL AREA POND | PROJECT 1 A PEKERJAAN ELEKTRIKALGENERAL AREA POND | LOW | 2025-02-10 | 2025-05-11 | 2025-06-15 | 21.91% | Belum Mulai | 2024-06-01 | 254 | 19.719 | 70.281 | 35 | 90 | -43 | 0.7164
3 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN ELEKTRIKAL | POND | POND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | PROJECT 1 A PEKERJAAN ELEKTRIKALPOND BLOCK 1‐C.1 s/d 2‐C.2 (typical) | LOW | 2024-12-16 | 2025-08-10 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 198 | 0 | 237 | -56 | 237 | 49 | 2.7883
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | AIR BERSIH | PROJECT 1 A PEKERJAAN MEKANIKALAIR BERSIH | HIGH | 2024-07-08 | 2025-08-10 | 2025-06-15 | 84.6% | Dalam Proses | 2024-06-01 | 37 | 336.708 | 61.292 | -56 | 398 | 49 | 0.24445
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | SEA WATER | PROJECT 1 A PEKERJAAN MEKANIKALSEA WATER | MEDIUM | 2025-04-07 | 2025-05-04 | 2025-06-15 | 28.98% | Belum Mulai | 2024-06-01 | 310 | 7.8246 | 19.1754 | 42 | 27 | -50 | 1.3834
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | GENERAL | GALIAN & TIMBUNAN PIPA | PROJECT 1 A PEKERJAAN MEKANIKALGALIAN & TIMBUNAN PIPA | LOW | 2025-04-07 | 2025-04-20 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 310 | 0 | 13 | 56 | 13 | -64 | 0.39134
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | POWE HOUSE | PROJECT 1 A PEKERJAAN MEKANIKALPOWE HOUSE | LOW | 2025-04-07 | 2025-06-23 | 2025-06-15 | 0.45% | Belum Mulai | 2024-06-01 | 310 | 0.3465 | 76.6535 | -8 | 77 | 1 | 0.10778
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESEARCH CENTRE ROOM | PROJECT 1 A PEKERJAAN MEKANIKALRESEARCH CENTRE ROOM | LOW | 2025-04-07 | 2025-06-22 | 2025-06-15 | 8.15% | Belum Mulai | 2024-06-01 | 310 | 6.194 | 69.806 | -7 | 76 | -1 | 0.0082318
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | IPAL | PROJECT 1 A PEKERJAAN MEKANIKALIPAL | LOW | 2024-09-09 | 2025-04-27 | 2025-06-15 | 20.58% | Belum Mulai | 2024-06-01 | 100 | 47.334 | 182.666 | 49 | 230 | -57 | 0.063041
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | FACILITY AREA | RESERVOIR SEA WATER INTAKE | PROJECT 1 A PEKERJAAN MEKANIKALRESERVOIR SEA WATER INTAKE | LOW | 2025-02-10 | 2025-03-09 | 2025-06-15 | 20.19% | Belum Mulai | 2024-06-01 | 254 | 5.4513 | 21.5487 | 98 | 27 | -106 | 0.035387
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | NURSERY POND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALNURSERY POND (4 UNIT) | LOW | 2024-12-16 | 2025-06-22 | 2025-06-15 | 16.6% | Belum Mulai | 2024-06-01 | 198 | 31.208 | 156.792 | -7 | 188 | -1 | 0.58542
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | MAIN POND (12 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALMAIN POND (12 UNIT) | MEDIUM | 2024-07-08 | 2025-06-08 | 2025-06-15 | 28.09% | Belum Mulai | 2024-06-01 | 37 | 94.1015 | 240.8985 | 7 | 335 | -15 | 18.9643
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | PROBIOTIK P[OND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALPROBIOTIK P[OND (4 UNIT) | LOW | 2025-01-13 | 2025-03-09 | 2025-06-15 | 7.68% | Belum Mulai | 2024-06-01 | 226 | 4.224 | 50.776 | 98 | 55 | -106 | 0.021883
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | SKIMMER POND (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALSKIMMER POND (4 UNIT) | MEDIUM | 2025-01-13 | 2025-02-09 | 2025-06-15 | 25.32% | Belum Mulai | 2024-06-01 | 226 | 6.8364 | 20.1636 | 126 | 27 | -134 | 0.10434
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | CONTROL ROOM (4 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALCONTROL ROOM (4 UNIT) | LOW | 2025-02-10 | 2025-04-27 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 254 | 0 | 76 | 49 | 76 | -57 | 1.65
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | OPERATOR HOUSE (2 UNIT) | PROJECT 1 A PEKERJAAN MEKANIKALOPERATOR HOUSE (2 UNIT) | LOW | 2025-04-07 | 2025-06-15 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 310 | 0 | 69 | 0 | 69 | -8 | 0.014876
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | POND AREA | GALIAN & TIM BUNAN PIPA (4 AREA) | PROJECT 1 A PEKERJAAN MEKANIKALGALIAN & TIM BUNAN PIPA (4 AREA) | LOW | 2025-05-05 | 2025-06-29 | 2025-06-15 | 0% | Belum Mulai | 2024-06-01 | 338 | 0 | 55 | -14 | 55 | 7 | 0.067955
4 | PROJECT 1 A | 231 049BOQ-Q-GEN-001 -4 | PEKERJAAN MEKANIKAL | OFFSHORE AREA | TRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | PROJECT 1 A PEKERJAAN MEKANIKALTRESTLE RESEARCH CENTRE ROOM & PLATFORM SWI | LOW | 2025-02-10 | 2025-03-09 | 2025-06-15 | 0.98% | Belum Mulai | 2024-06-01 | 254 | 0.2646 | 26.7354 | 98 | 27 | -106 | 0.24341
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | GENERAL | GENERAL | PROJECT 1 BPEKERJAAN STRUKTURGENERAL | MEDIUM | 2024-08-12 | 2025-10-12 | 2025-06-15 | 48.49% | Dalam Proses | 2024-08-01 | 11 | 206.5597 | 219.4403 | -119 | 426 | 112 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN STRUKTURGUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-06-15 | 100% | Selesai | 2024-08-01 | 11 | 426 | 0 | -119 | 426 | 112 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN STRUKTURGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Belum Mulai | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN STRUKTURFEED WAREHOUSE | HIGH | 2025-04-15 | 2025-06-08 | 2025-06-15 | 89.02% | Dalam Proses | 2024-08-01 | 257 | 48.073 | 5.927 | 7 | 54 | -15 | 7.3157
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN STRUKTURLABORATORIUM | MEDIUM | 2025-04-15 | 2025-07-27 | 2025-06-15 | 47.02% | Dalam Proses | 2024-08-01 | 257 | 48.4256 | 54.5744 | -42 | 103 | 35 | 1.2678
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | PROJECT 1 BPEKERJAAN STRUKTURWATER TOWER 1 | HIGH | 2025-05-05 | 2025-05-25 | 2025-06-15 | 100% | Belum Mulai | 2024-08-01 | 277 | 20 | 0 | 21 | 20 | -29 | 0.90362
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WATER TOWER 1 | PROJECT 1 BPEKERJAAN STRUKTURWATER TOWER 1 | HIGH | 2025-05-05 | 2025-05-25 | 2025-06-15 | 100% | Terlambat | 2024-08-01 | 277 | 20 | 0 | 21 | 20 | -29 | 0.90362
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GUARD TOWER | PROJECT 1 BPEKERJAAN STRUKTURGUARD TOWER | MEDIUM | 2025-04-21 | 2025-06-15 | 2025-06-15 | 28.55% | Dalam Proses | 2024-08-01 | 263 | 15.7029 | 39.2971 | 0 | 55 | -8 | 0.90362
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN STRUKTURKANTIN | HIGH | 2025-04-21 | 2025-07-20 | 2025-06-15 | 96.84% | Dalam Proses | 2024-08-01 | 263 | 87.1575 | 2.8425 | -35 | 90 | 28 | 1.5819
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN STRUKTURFAMILY STAFF HOUSE | LOW | 2025-04-21 | 2025-08-24 | 2025-06-15 | 7.187% | Dalam Proses | 2024-08-01 | 263 | 8.9844 | 116.0156 | -70 | 125 | 63 | 1.2842
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN STRUKTURWORKSHOP | HIGH | 2025-04-28 | 2025-07-27 | 2025-06-15 | 97.04% | Dalam Proses | 2024-08-01 | 270 | 87.3349 | 2.6651 | -42 | 90 | 35 | 6.1842
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN STRUKTURMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN STRUKTURPUMP HOUSE | HIGH | 2025-05-05 | 2025-07-13 | 2025-06-15 | 64.44% | Dalam Proses | 2024-08-01 | 277 | 44.4636 | 24.5364 | -28 | 69 | 21 | 0.94074
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN STRUKTURDORMITORY FEMALE | HIGH | 2025-04-28 | 2025-08-17 | 2025-06-15 | 62.58% | Dalam Proses | 2024-08-01 | 270 | 69.464 | 41.536 | -63 | 111 | 56 | 1.2317
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN STRUKTURDORMITORY MALE | LOW | 2024-10-28 | 2025-08-10 | 2025-06-15 | 15.86% | Dalam Proses | 2024-08-01 | 88 | 45.3596 | 240.6404 | -56 | 286 | 49 | 4.3412
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GAZEBOO | PROJECT 1 BPEKERJAAN STRUKTURGAZEBOO | HIGH | 2025-06-02 | 2025-06-22 | 2025-06-15 | 87.44% | Terlambat | 2024-08-01 | 305 | 17.4885 | 2.5115 | -7 | 20 | -1 | 0.012874
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN STRUKTURGARDU HUB | LOW | 2025-04-15 | 2025-05-17 | 2025-06-15 | 12.41% | Dalam Proses | 2024-08-01 | 257 | 3.9712 | 28.0288 | 29 | 32 | -37 | 0.87756
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN STRUKTURWEIGHT HOUSE | MEDIUM | 2025-05-05 | 2025-07-13 | 2025-06-15 | 54.24% | Dalam Proses | 2024-08-01 | 277 | 37.4262 | 31.5738 | -28 | 69 | 21 | 5.6464
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN STRUKTUROFFICE | HIGH | 2025-04-15 | 2025-07-20 | 2025-06-15 | 88.59% | Dalam Proses | 2024-08-01 | 257 | 85.051 | 10.949 | -35 | 96 | 28 | 3.3921
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | TPS | PROJECT 1 BPEKERJAAN STRUKTURTPS | LOW | 2025-05-05 | 2025-08-10 | 2025-06-15 | 23.73% | Dalam Proses | 2024-08-01 | 277 | 23.0224 | 73.9776 | -56 | 97 | 49 | 1.1565
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | FACILITY AREA | MAIN GATE | PROJECT 1 BPEKERJAAN STRUKTURMAIN GATE | LOW | 2025-04-28 | 2025-08-22 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 270 | 0 | 116 | -68 | 116 | 61 | 0.35948
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN STRUKTURGUEST HOUSE | LOW | 2024-08-12 | 2025-07-13 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 335 | -28 | 335 | 21 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN STRUKTURPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
1 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN STRUKTUR | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN STRUKTURVVIP HOUSE | LOW | 2025-04-15 | 2025-08-31 | 2025-06-15 | 11.5% | Terlambat | 2024-08-01 | 257 | 15.8736 | 122.1264 | -77 | 138 | 70 | 7.3681
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN ARSITEKTURLABORATORIUM | LOW | 2025-07-21 | 2025-08-24 | 2025-06-15 | 8.171% | Belum Mulai | 2024-08-01 | 354 | 2.778 | 31.222 | -70 | 34 | 63 | 1.9262
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN ARSITEKTURGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Belum Mulai | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURFEED WAREHOUSE | LOW | 2025-05-19 | 2025-06-06 | 2025-06-15 | 14.41% | Terlambat | 2024-08-01 | 291 | 2.5938 | 15.4062 | 9 | 18 | -17 | 2.6948
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN ARSITEKTURDORMITORY MALE | LOW | 2025-06-30 | 2025-09-07 | 2025-06-15 | 8.221% | Terlambat | 2024-08-01 | 333 | 5.6728 | 63.3272 | -84 | 69 | 77 | 7.1456
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN ARSITEKTURKANTIN | MEDIUM | 2025-06-16 | 2025-08-17 | 2025-06-15 | 39.4% | Dalam Proses | 2024-08-01 | 319 | 24.4293 | 37.5707 | -63 | 62 | 56 | 2.1251
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN ARSITEKTURWORKSHOP | HIGH | 2025-06-23 | 2024-08-10 | 2025-06-15 | 63.66% | Terlambat | 2024-08-01 | 326 | -201.7943 | -115.2057 | 309 | -317 | -317 | 2.2141
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURFAMILY STAFF HOUSE | LOW | 2025-07-07 | 2025-09-30 | 2025-06-15 | 4.05% | Terlambat | 2024-08-01 | 340 | 3.4425 | 81.5575 | -107 | 85 | 100 | 2.1434
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN ARSITEKTURMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN ARSITEKTUROFFICE | MEDIUM | 2025-06-16 | 2025-08-03 | 2025-06-15 | 43.54% | Dalam Proses | 2024-08-01 | 319 | 20.898 | 27.102 | -49 | 48 | 42 | 4.2092
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURWEIGHT HOUSE | LOW | 2025-06-09 | 2025-07-27 | 2025-06-15 | 21.69% | Belum Mulai | 2024-08-01 | 312 | 10.4112 | 37.5888 | -42 | 48 | 35 | 0.67907
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GAZEBOO (BY VENDOR) | PROJECT 1 BPEKERJAAN ARSITEKTURGAZEBOO (BY VENDOR) | LOW | 2025-06-23 | 2025-07-06 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 326 | 0 | 13 | -21 | 13 | 14 | 0.37058
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURPUMP HOUSE | MEDIUM | 2025-05-19 | 2025-07-27 | 2025-06-15 | 58.79% | Terlambat | 2024-08-01 | 291 | 40.5651 | 28.4349 | -42 | 69 | 35 | 0.46783
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN ARSITEKTURDORMITORY FEMALE | MEDIUM | 2025-07-07 | 2025-05-31 | 2025-06-15 | 46.49% | Dalam Proses | 2024-08-01 | 340 | -17.2027 | -19.7973 | 15 | -37 | -23 | 2.1434
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN ARSITEKTURGUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-06-15 | 100% | Selesai | 2024-08-01 | 11 | 426 | 0 | -119 | 426 | 112 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | TPS | PROJECT 1 BPEKERJAAN ARSITEKTURTPS | LOW | 2025-06-30 | 2025-08-31 | 2025-06-15 | 16.26% | Terlambat | 2024-08-01 | 333 | 10.0812 | 51.9188 | -77 | 62 | 70 | 0.6683
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | MAIN GATE | PROJECT 1 BPEKERJAAN ARSITEKTURMAIN GATE | LOW | 2025-06-16 | 2025-07-20 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 319 | 0 | 34 | -35 | 34 | 28 | 0.4509
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN ARSITEKTURGARDU HUB | LOW | 2025-06-02 | 2025-07-13 | 2025-06-15 | 8.12% | Terlambat | 2024-08-01 | 305 | 3.3292 | 37.6708 | -28 | 41 | 21 | 0.47544
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURVVIP HOUSE | LOW | 2025-07-28 | 2025-09-30 | 2025-06-15 | 9.14% | Terlambat | 2024-08-01 | 361 | 5.8496 | 58.1504 | -107 | 64 | 100 | 7.4012
2 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ARSITEKTUR | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN ARSITEKTURGUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN MEKANIKALLABORATORIUM | LOW | 2025-07-28 | 2025-09-07 | 2025-06-15 | 0% | Belum Mulai | 2024-08-01 | 361 | 0 | 41 | -84 | 41 | 77 | 0.1253
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN MEKANIKALGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN MEKANIKALDORMITORY MALE | LOW | 2025-07-07 | 2025-07-27 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 340 | 0 | 20 | -42 | 20 | 35 | 0.53564
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN MEKANIKALKANTIN | LOW | 2025-07-14 | 2025-08-03 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 347 | 0 | 20 | -49 | 20 | 42 | 0.31366
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALFAMILY STAFF HOUSE | LOW | 2025-07-28 | 2025-08-17 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 361 | 0 | 20 | -63 | 20 | 56 | 0.15028
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN MEKANIKALMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN MEKANIKALOFFICE | LOW | 2025-06-23 | 2025-07-06 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 326 | 0 | 13 | -21 | 13 | 14 | 0.16406
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN MEKANIKALDORMITORY FEMALE | LOW | 2025-07-14 | 2025-07-20 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 347 | 0 | 6 | -35 | 6 | 28 | 0.15028
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN MEKANIKALGUARD HOUSE 1 | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER POND AREA | PROJECT 1 BPEKERJAAN MEKANIKALWATER TOWER POND AREA | LOW | 2025-05-26 | 2025-06-08 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 298 | 0 | 13 | 7 | 13 | -15 | 0.41311
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | FACILITY AREA | WATER TOWER FACILITY AREA | PROJECT 1 BPEKERJAAN MEKANIKALWATER TOWER FACILITY AREA | LOW | 2025-05-26 | 2025-06-08 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 298 | 0 | 13 | 7 | 13 | -15 | 0.41311
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALVVIP HOUSE | LOW | 2025-08-04 | 2025-08-24 | 2025-06-15 | 0% | Belum Mulai | 2024-08-01 | 368 | 0 | 20 | -70 | 20 | 63 | 0.71591
3 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN MEKANIKAL | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN MEKANIKALGUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | PRIVATE HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALPRIVATE HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | VVIP HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALVVIP HOUSE | LOW | 2025-09-01 | 2025-09-21 | 2025-06-15 | 24.28% | Belum Mulai | 2024-08-01 | 396 | 4.856 | 15.144 | -98 | 20 | 91 | 1.1364
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | PRIVATE AREA | GUEST HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALGUEST HOUSE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | KANTIN | PROJECT 1 BPEKERJAAN ELEKTRIKALKANTIN | LOW | 2025-08-25 | 2025-09-14 | 2025-06-15 | 22.28% | Terlambat | 2024-08-01 | 389 | 4.456 | 15.544 | -91 | 20 | 84 | 0.86889
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | LABORATORIUM | PROJECT 1 BPEKERJAAN ELEKTRIKALLABORATORIUM | MEDIUM | 2025-09-01 | 2025-09-30 | 2025-06-15 | 27.02% | Terlambat | 2024-08-01 | 396 | 7.8358 | 21.1642 | -107 | 29 | 100 | 1.9102
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | OFFICE | PROJECT 1 BPEKERJAAN ELEKTRIKALOFFICE | LOW | 2025-07-07 | 2025-07-20 | 2025-06-15 | 20.08% | Belum Mulai | 2024-08-01 | 340 | 2.6104 | 10.3896 | -35 | 13 | 28 | 2.3615
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | MOSQUE | PROJECT 1 BPEKERJAAN ELEKTRIKALMOSQUE | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Dalam Proses | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 1 | PROJECT 1 BPEKERJAAN ELEKTRIKALGUARD HOUSE 1 | HIGH | 2024-08-12 | 2025-10-12 | 2025-06-15 | 100% | Selesai | 2024-08-01 | 11 | 426 | 0 | -119 | 426 | 112 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GUARD HOUSE 2 | PROJECT 1 BPEKERJAAN ELEKTRIKALGUARD HOUSE 2 | LOW | 2024-08-12 | 2025-10-12 | 2025-06-15 | 0% | Belum Mulai | 2024-08-01 | 11 | 0 | 426 | -119 | 426 | 112 | 0
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WORKSHOP | PROJECT 1 BPEKERJAAN ELEKTRIKALWORKSHOP | MEDIUM | 2025-08-11 | 2025-08-31 | 2025-06-15 | 25.43% | Terlambat | 2024-08-01 | 375 | 5.086 | 14.914 | -77 | 20 | 70 | 1.2773
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FEED WAREHOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALFEED WAREHOUSE | MEDIUM | 2025-07-07 | 2025-07-27 | 2025-06-15 | 26.07% | Terlambat | 2024-08-01 | 340 | 5.214 | 14.786 | -42 | 20 | 35 | 1.3022
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY MALE | PROJECT 1 BPEKERJAAN ELEKTRIKALDORMITORY MALE | LOW | 2025-09-01 | 2025-09-30 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 396 | 0 | 29 | -107 | 29 | 100 | 2.2106
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | WEIGHT HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALWEIGHT HOUSE | MEDIUM | 2025-06-16 | 2025-06-29 | 2025-06-15 | 25.93% | Terlambat | 2024-08-01 | 319 | 3.3709 | 9.6291 | -14 | 13 | 7 | 0.9409
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GAZEBOO | PROJECT 1 BPEKERJAAN ELEKTRIKALGAZEBOO | MEDIUM | 2025-07-07 | 2025-08-03 | 2025-06-15 | 30% | Belum Mulai | 2024-08-01 | 340 | 8.1 | 18.9 | -49 | 27 | 42 | 0.8322
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | FAMILY STAFF HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALFAMILY STAFF HOUSE | LOW | 2025-09-22 | 2025-09-30 | 2025-06-15 | 0% | Terlambat | 2024-08-01 | 417 | 0 | 8 | -107 | 8 | 100 | 1.143
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | DORMITORY FEMALE | PROJECT 1 BPEKERJAAN ELEKTRIKALDORMITORY FEMALE | LOW | 2025-09-01 | 2025-08-24 | 2025-06-15 | 24.25% | Terlambat | 2024-08-01 | 396 | -1.94 | -6.06 | -70 | -8 | 63 | 0.65729
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | PUMP HOUSE | PROJECT 1 BPEKERJAAN ELEKTRIKALPUMP HOUSE | LOW | 2025-07-28 | 2025-08-24 | 2025-06-15 | 24.97% | Terlambat | 2024-08-01 | 361 | 6.7419 | 20.2581 | -70 | 27 | 63 | 1.1354
4 | PROJECT 1 B | 231049-BOQ-Q-GEN-002-4 | PEKERJAAN ELEKTRIKAL | FACILITY AREA | GARDU HUB | PROJECT 1 BPEKERJAAN ELEKTRIKALGARDU HUB | MEDIUM | 2025-06-30 | 2025-07-13 | 2025-06-15 | 30% | Belum Mulai | 2024-08-01 | 333 | 3.9 | 9.1 | -28 | 13 | 21 | 0.45616